## Shopping Cart
Bug ID | Related Test Case | Bug Title | Preconditions | Steps to Recreate | Test Data | Environment | Priority | Severity | Expected Result | Actual Result | Status | Attachaments
SC-Bug-001 | SC11 | The product image doesn't show in the shopping cart | 1. User is logged in 2. Products added to cart | 1. navigate to the cart content page 2. confirm that the product image is displayed | Product: “Sauce Labs Backpack” | Chrome Version 141.0.7390.123 | High | Critical | User see the added items and each item's image next to it | The system doesn't display the images of products in the cart | Open
SC-Bug-002 | SC16 | The total price of products in the cart isn't displayed | 1. User is logged in 2. Products added to cart | 1. navigate to the cart content page 2. confirm that the total price of items in the cart is displayed | Product: “Sauce Labs Backpack”, "Sauce Labs Bike Light" | Chrome Version 141.0.7390.123 | High | Critical | User find the total price of the products displayed | The system doesn't display the total price of products in the cart | Open
SC-Bug-003 | SC17 | Users share cart content | 1. User is logged in | 1. Add items to cart 2. Log out 3. Log in with a new user 4. check the cart content | First user name: standard_user Second user name: problem_user Product: “Sauce Labs Backpack” | Chrome Version 141.0.7390.123 | High | Critical | User find the new cart empty | The cart still carry the same products from previous user | Open
SC-Bug-004 | SC19 | Cart isn't empty after logout | 1. User is logged in | 1. Add products to cart 2. Logout 3. Login again | Products: “Sauce Labs Backpack” | Chrome Version 141.0.7390.123 | Low | Major | Cart Should be empty | The cart still carry the same products | Open
SC-Bug-005 | SC20 | Can't add more than one from the same product | 1. User is logged in | 1. Add a product to cart 2. try to add the same product again | Products: “Sauce Labs Backpack” | Products: “Sauce Labs Backpack” | High | Critical | user should be able to add more than one from the same item | user can add the product only one time and can't choose quantity | Open

## Checkout
Bug ID | Related Test Case | Bug Title | Preconditions | Steps to Recreate | Test Data | Environment | Priority | Severity | Expected Result | Actual Result | Status | Attachaments
CO-Bug-001 | CO19 | Invalid postal code work like valid postal code | 1. Internet is up 2. User is Logged in | 1. Add product to cart 2. Go to checkout 3. Enter invalid Postal (More than 7 digits) 4. Submit | First Name: John Last Name: Smith Postal: ABC1235 | Chrome Version 141.0.7390.123 | High | Critical | Error message shown for invalid Postal | User is redirected to overview page | Open
CO-Bug-002 | CO21 | Cancel checkout from overview page doesn't redirect to shopping cart page | 1. Internet is up 2. User is Logged in | 1. Add product to cart 2. proceed to checkout 3. enter valid details 4. click "continue" button 5. Go to checkout overview page 6. Click" Cancel" button | Product: “Sauce Labs Backpack” First Name: John Last Name: Smith Postal: 12345 | Chrome Version 141.0.7390.123 | medium | Medium | User is redirected to cart page | User is redirected to Home page | Open
CO-Bug-003 | CO28 | The product image doesn't appear in checkout overview page | 1. Internet is up 2. User is Logged in | 1. Add product to cart 2. proceed to checkout 3. enter valid details 4. click "continue" button 5. Go to checkout overview page 6. confirm that the product image is displayed correctly | Product: “Sauce Labs Backpack” First Name: John Last Name: Smith Postal: 12345 | Chrome Version 141.0.7390.123 | High | Critical | User see the added items and each item's image next to it | User can't see the each item's image next to it | Open